## Yr&quarter
Year/quarter (financial year)
|  |  | Plan |  |  | Actual |  |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  | 25
Ref | Activity/integration | Start | Duration (qurtrs) | Funding | Start | Duration (qurtrs) | Funding | All ctrs | Deployed | All ctrs % | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | CPCS IT | 21 Q1 | 3 |  | 21 Q1 | 4 |  | 11300 | 0 | xx % | bar: 21 Q1 to 21 Q3
2 | DMS API | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 | 0 | xx % | bar: 21 Q2 to 21 Q3
3 | CPCF future srvs | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx % | bar: 21 Q2 to 21 Q3
4 | EPS FHIR/chg/Tracker | 21 Q1 | 16 |  | 21 Q1 | 2 |  | 11300 | 0 | xx % | bar: 21 Q1 to 22 Q3
5 | PRSB stnds | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx % | bar: 21 Q1 to 22 Q3
6 | GP Connect | 21 Q1 | 2 |  | 21 Q1 | 11 |  | 11300 | 0 | xx % | bar: 22 Q1 to 22 Q3
7 | SCR AI 1-click | 21 Q1 | 2 |  | 21 Q1 | 13 |  | 11300 | 0 | xx %
8 | NHS booking | 21 Q1 | 9 |  | 21 Q1 | 5 |  | 11300 | 0 | xx %
9 | NHS referral | 21 Q1 | 1 |  | 21 Q1 | 6 |  | 11300 | 0 | xx %
10 | NHS App / Login | 21 Q1 | 7 |  | 21 Q1 | 11 |  | 11300 | 0 | xx %
11 | CIS 2 / Virtual SCs | 21 Q1 | 3 |  | 21 Q1 | 4 |  | 11300 | 0 | xx %
12 | Video con | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
13 | RTEC | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
14 | Mobiles (PMR+NHS) | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
16 | MYS | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
17 | LHCRs | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
18 | ITK2 | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
19 | Clinical info & UI+ | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
20 | 4 nations work | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx %
21 | National Record Locator | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx %
22 | PMR wishlist + requests/oth | 21 Q1 | 1 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
Community Pharmacy IT Group : NHS IT / system projects template chart
This template chart lists some key projects and is not comprehensive. It is not listed by priority. The populated timelines are example ones.

## Yr&month
Year/month (financial year)
|  |  | Plan |  |  | Actual |  |  |  |  | 21 | [11 empty] | 22
Ref | Activity/integration | Start | Duration (qurtrs) | Funding | Start | Duration (qurtrs) | Funding | All ctrs | Deployed | All ctrs % | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | CPCS IT | 21 Q1 | 3 |  | 21 Q1 | 4 |  | 11300 | 0 | xx % | bar: 21 1 to 21 3
2 | DMS API | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 | 0 | xx % | bar: 21 2 to 21 3
3 | CPCF future srvs | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx % | bar: 21 2 to 21 3
4 | EPS FHIR/chg/Tracker | 21 Q1 | 16 |  | 21 Q1 | 2 |  | 11300 | 0 | xx % | bar: 21 1 to 21 7
5 | PRSB stnds | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx % | bar: 21 1 to 21 7
6 | GP Connect | 21 Q1 | 2 |  | 21 Q1 | 11 |  | 11300 | 0 | xx % | bar: 21 5 to 21 7
7 | SCR AI 1-click | 21 Q1 | 2 |  | 21 Q1 | 13 |  | 11300 | 0 | xx %
8 | NHS booking | 21 Q1 | 9 |  | 21 Q1 | 5 |  | 11300 | 0 | xx %
9 | NHS referral | 21 Q1 | 1 |  | 21 Q1 | 6 |  | 11300 | 0 | xx %
10 | NHS App / Login | 21 Q1 | 7 |  | 21 Q1 | 11 |  | 11300 | 0 | xx %
11 | CIS 2 / Virtual SCs | 21 Q1 | 3 |  | 21 Q1 | 4 |  | 11300 | 0 | xx %
12 | Video con | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
13 | RTEC | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
14 | Mobiles (PMR+NHS) | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
16 | MYS | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
17 | LHCRs | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
18 | ITK2 | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
19 | Clinical info & UI+ | 21 Q1 | 2 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
20 | 4 nations work | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx %
21 | National Record Locator | 21 Q1 | 2 |  | 21 Q1 | 4 |  | 11300 |  | xx %
22 | PMR wishlist + requests/oth | 21 Q1 | 1 |  | 21 Q1 | 1 |  | 11300 | 0 | xx %
Community Pharmacy IT Group : NHS IT / system projects template chart
This template chart lists some key projects and is not comprehensive. It is not listed by priority. The populated timelines are example ones.

## Notes
This CP ITG gantt chart representing example activities to be performed along with the duration and degree of completion, to be used as per the need – if useful for the CP ITG and/or individual system suppliers or other IT project teams. This template chart lists some key projects and is not comprehensive. It is not listed by priority. The populated timelines are example ones.